## pradhanmantri aawas yojna san 2
A.2 House progress against the target financial year | As On: 12/11/2025 22:04:41
#SNo | Village | Reg. No. | Beneficiary Name | Father's/Mother's Name | House Alloted To | Sanction No. | Sanctioned Amount | Installment Paid | Amount Released | House Status
1 | DEURBK | MH122456309 | Subhash Ananda Deore |  | Joint(Husband and Wife) | MH07001/4/3536[15-04-2022] | 120000 | 4 | 120000 | Completed
2 | DEURBK | MH122546930 | Prakash Motiram Deore |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 4 | 120000 | Completed
3 | DEURBK | MH122580392 | Ashabai Mahendra Deore |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 4 | 120000 | Completed
4 | DEURBK | MH122925414 | dilip bhagachand bagale |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 4 | 120000 | Completed
5 | DEURBK | MH123222052 | bhikan ukhadu chavhan |  | Joint(Husband and Wife) | MH07001/1/3576[20-04-2022] | 120000 | 2 | 60000 | Completed
6 | DEURBK | MH123323759 | naval prabhakar paradhi |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 4 | 120000 | Completed
7 | DEURBK | MH123327127 | dilip balu gayakawad |  | Joint(Husband and Wife) | MH07001/1/3576[20-04-2022] | 120000 | 3 | 100000 | Completed
8 | DEURBK | MH123331189 | nanabhau surasing borase |  | Joint(Husband and Wife) | MH07001/1/3487[08-04-2022] | 120000 | 4 | 120000 | Completed
9 | DEURBK | MH123336337 | Shantaram dhudaku khairnar |  | Joint(Husband and Wife) | MH07001/4/3733[01-05-2022] | 120000 | 4 | 120000 | Completed
10 | DEURBK | MH123339519 | bhaskar budha Deore |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 3 | 115000 | Completed
11 | DEURBK | MH123605316 | ramesh kashinath shewale |  | Joint(Husband and Wife) | MH07001/4/5717[24-09-2024] | 120000 | 2 | 85000 | Plinth
12 | DEURBK | MH123808013 | Bhadane Bapu Rambhau |  | Joint(Husband and Wife) | MH07001/4/3536[15-04-2022] | 120000 | 4 | 120000 | Completed
13 | DEURBK | MH125355086 | sunil fakira mali |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 4 | 120000 | Completed
14 | DEURBK | MH125626772 | Aananda Rohidas Pardhi |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 4 | 120000 | Completed
15 | DEURBK | MH125869476 | Bhatabai kashinath Gavale |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 1 | 15000 | Completed
16 | DEURBK | MH126592709 | shriram hiraman gayakwad |  | Joint(Husband and Wife) | MH07001/1/4602[08-09-2024] | 120000 | 3 | 115000 | Lintel Level
17 | DEURBK | MH126813543 | Shindubai |  | Joint(Husband and Wife) | MH07001/1/3797[07-05-2022] | 120000 | 4 | 120000 | Completed
18 | DEURBK | MH127218127 | Chitram Shiva Gayakwad |  | Joint(Husband and Wife) | MH07001/1/4431[06-01-2023] | 120000 | 3 | 115000 | Completed
19 | DEURBK | MH127244853 | darasing uttam panpatil |  | Joint(Husband and Wife) | MH07001/2/3577[20-04-2022] | 120000 | 2 | 85000 | Completed
20 | DEURBK | MH127319111 | samadhan aba malache |  | Joint(Husband and Wife) | MH07001/1/3868[13-05-2022] | 120000 | 3 | 115000 | Completed
21 | DEURBK | MH127466401 | Rupabai Kashinath Naik |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 3 | 100000 | Completed
22 | DEURBK | MH129035662 | narendr jagannath sonar |  | Joint(Husband and Wife) | MH07001/4/3423[04-04-2022] | 120000 | 4 | 120000 | Completed
23 | DEURBK | MH129077035 | aba daga suryawanshi |  | Joint(Husband and Wife) | MH07001/4/3423[04-04-2022] | 120000 | 2 | 60000 | Completed
24 | DEURBK | MH130114859 | Pawar Santosh Ramdas |  | Joint(Husband and Wife) | MH07001/1/3732[01-05-2022] | 120000 | 4 | 120000 | Completed
25 | DEURBK | MH130512651 | Latabai Eknath Thakur |  | Joint(Husband and Wife) | MH07001/1/3604[21-04-2022] | 120000 | 4 | 120000 | Completed
26 | DEURBK | MH130517645 | Bhaidas Shamrao Gayakwad |  | Joint(Husband and Wife) | MH07001/1/5716[24-09-2024] | 120000 |  |  | House Sanctioned
27 | DEURBK | MH130524523 | Dilip Bhuda Koli |  | Joint(Husband and Wife) | MH07001/1/5716[24-09-2024] | 120000 | 3 | 115000 | Completed
28 | DEURBK | MH130524563 | Ashok Shamrao Koli |  | Joint(Husband and Wife) | MH07001/1/3732[01-05-2022] | 120000 | 4 | 120000 | Completed
29 | DEURBK | MH130828189 | Dilip Mahadu Sonwane |  | Joint(Husband and Wife) | MH07001/1/4166[23-06-2022] | 120000 | 4 | 120000 | Completed
30 | DEURBK | MH130828203 | Mahendra Suresh Deore |  | Joint(Husband and Wife) | MH07001/4/4432[06-01-2023] | 120000 | 4 | 120000 | Completed
31 | DEURBK | MH130828211 | Sahebrao Vittal Borse |  | Joint(Husband and Wife) | MH07001/1/5716[24-09-2024] | 120000 | 2 | 85000 | Plinth
32 | DEURBK | MH130828225 | Ashok Shivram Sonwane |  | Joint(Husband and Wife) | MH07001/1/3868[13-05-2022] | 120000 | 4 | 120000 | Completed
33 | DEURBK | MH130829030 | Kishor Lotan Shewale |  | Joint(Husband and Wife) | MH07001/4/5717[24-09-2024] | 120000 | 3 | 115000 | Lintel Level
34 | DEURBK | MH130829140 | Ratan Ramdas Gayakwd |  | Joint(Husband and Wife) | MH07001/1/4166[23-06-2022] | 120000 | 2 | 60000 | Completed
35 | DEURBK | MH130829314 | Ramchandr Buda Thakur |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 4 | 120000 | Completed
36 | DEURBK | MH130829515 | Nitin Dadaji Salunkhe |  | Joint(Husband and Wife) | MH07001/1/3868[13-05-2022] | 120000 | 4 | 120000 | Completed
37 | DEURBK | MH130889367 | Gujarnbai Babaji Borse |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 4 | 120000 | Completed
38 | DEURBK | MH130889423 | Bapu Nana More |  | Joint(Husband and Wife) | MH07001/1/5716[24-09-2024] | 120000 | 3 | 115000 | Lintel Level
39 | DEURBK | MH130889439 | Laxman sukdev Bors3 |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 3 | 100000 | Completed
40 | DEURBK | MH130889878 | Himmat Ukha Salunke |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 4 | 120000 | Completed
41 | DEURBK | MH130889885 | Gagannath Ramchandr Gavale |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 3 | 115000 | Completed
42 | DEURBK | MH130941505 | Deva Keshav Shinde |  | Joint(Husband and Wife) | MH07001/1/5716[24-09-2024] | 120000 | 3 | 115000 | Completed
43 | DEURBK | MH130949678 | Bavrav Suka Borse |  | Joint(Husband and Wife) | MH07001/1/4166[23-06-2022] | 120000 | 4 | 120000 | Completed
44 | DEURBK | MH130952514 | Latabai Eknath Pawar |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 4 | 120000 | Completed
45 | DEURBK | MH131063685 | girdhar bhavrao Deore |  | Joint(Husband and Wife) | MH07001/4/3423[04-04-2022] | 120000 | 4 | 120000 | Completed
46 | DEURBK | MH131063705 | shankar Pundalik Deore |  | Joint(Husband and Wife) | MH07001/4/3423[04-04-2022] | 120000 | 3 | 115000 | Completed
47 | DEURBK | MH131264675 | jayavant sonu nerkar |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 4 | 120000 | Completed
48 | DEURBK | MH131267357 | gorakh pundalik Deore |  | Joint(Husband and Wife) | MH07001/4/3702[28-04-2022] | 120000 | 4 | 120000 | Completed
49 | DEURBK | MH131289109 | Dipchand Santosh Thakare |  | Joint(Husband and Wife) | MH07001/4/3613[21-04-2022] | 120000 | 4 | 120000 | Completed
50 | DEURBK | MH131311395 | Shivram Natu Wagh |  | Joint(Husband and Wife) | MH07001/1/3868[13-05-2022] | 120000 | 4 | 120000 | Completed
51 | DEURBK | MH131618824 | Pratibha Kailas Nerkar |  | Joint(Husband and Wife) | MH07001/4/4432[06-01-2023] | 120000 | 2 | 85000 | Completed
52 | DEURBK | MH131619169 | Raju Sada Ahire |  | Joint(Husband and Wife) | MH07001/1/3868[13-05-2022] | 120000 | 2 | 85000 | Completed
53 | DEURBK | MH131740731 | Mangu Bansi Malche |  | Joint(Husband and Wife) | MH07001/1/3612[21-04-2022] | 120000 | 4 | 120000 | Completed
54 | DEURBK | MH131741682 | Nerkar Chaya Nana |  | Joint(Husband and Wife) | MH07001/2/4167[23-06-2022] | 120000 | 4 | 120000 | Completed
55 | DEURBK | MH131741806 | Sarita Raju Deore |  | Joint(Husband and Wife) | MH07001/4/3536[15-04-2022] | 120000 | 4 | 120000 | Completed
56 | DEURBK | MH132376710 | mahendr hiraman ahirrao |  | Joint(Husband and Wife) | MH07001/4/4964[11-09-2024] | 120000 | 3 | 115000 | Completed
57 | DEURBK | MH132377607 | jijabai dasharath Deore |  | Joint(Husband and Wife) | MH07001/3/4553[08-09-2024] | 120000 | 2 | 85000 | Lintel Level
58 | DEURBK | MH132453346 | indubai sahebrao borase |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 3 | 115000 | Completed
59 | DEURBK | MH132883432 | jijabai gulab patil |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 3 | 115000 | Completed
60 | DEURBK | MH133030059 | sushilabai ananda borse |  | Joint(Husband and Wife) | MH07001/1/3487[08-04-2022] | 120000 | 3 | 100000 | Completed
61 | DEURBK | MH133030074 | bhivalabai sadashiv borse |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 3 | 100000 | Completed
62 | DEURBK | MH133056515 | naval daval sonawne |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 1 | 15000 | Completed
63 | DEURBK | MH133409608 | dinesh girdhar bhadane |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 4 | 120000 | Completed
64 | DEURBK | MH134018171 | ravindra ananda deore |  | Joint(Husband and Wife) | MH07001/4/6678[29-01-2025] | 120000 | 2 | 85000 | Plinth
65 | DEURBK | MH134018473 | dashrath nanabhau bhamre |  | Joint(Husband and Wife) | MH07001/3/4553[08-09-2024] | 120000 | 3 | 115000 | Lintel Level
66 | DEURBK | MH134188032 | kishor jivan shirsath |  | Joint(Husband and Wife) | MH07001/1/4962[11-09-2024] | 120000 | 3 | 115000 | Lintel Level
67 | DEURBK | MH134258023 | Ukubai ramchandra nerkar |  | Joint(Husband and Wife) | MH07001/2/4251[22-07-2022] | 120000 | 4 | 120000 | Completed
68 | DEURBK | MH134258047 | Mandabai Devachand Nerkar |  | Joint(Husband and Wife) | MH07001/2/4251[22-07-2022] | 120000 | 4 | 120000 | Completed
69 | DEURBK | MH134364319 | jijabai nimba shewale |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 4 | 120000 | Completed
70 | DEURBK | MH134493018 | nhanu pandu pardhi |  | Joint(Husband and Wife) | MH07001/1/3487[08-04-2022] | 120000 | 4 | 120000 | Completed
71 | DEURBK | MH134833978 | sunil gambhir borse |  | Joint(Husband and Wife) | MH07001/1/4962[11-09-2024] | 120000 | 3 | 115000 | Lintel Level
72 | DEURBK | MH135201548 | shama bhatu more |  | Joint(Husband and Wife) | MH07001/1/3487[08-04-2022] | 120000 | 2 | 85000 | Completed
73 | DEURBK | MH135508123 | hiraman arun dabhade |  | Joint(Husband and Wife) | MH07001/1/3576[20-04-2022] | 120000 | 4 | 120000 | Completed
74 | DEURBK | MH135648027 | Tapabai bhta salunke |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 1 | 15000 | Completed
75 | DEURBK | MH136016293 | uttam polad more |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 4 | 120000 | Completed
76 | DEURBK | MH136016294 | ratna murlidhar paradhi |  | Joint(Husband and Wife) | MH07001/1/3980[27-05-2022] | 120000 | 4 | 120000 | Completed
77 | DEURBK | MH136072931 | sukdev sampat borse |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 3 | 100000 | Completed
78 | DEURBK | MH136115148 | Buatabai Harchand Ahire |  | Joint(Husband and Wife) | MH07001/1/3732[01-05-2022] | 120000 | 4 | 120000 | Completed
79 | DEURBK | MH136371499 | ravan punju borse |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 3 | 100000 | Completed
80 | DEURBK | MH136371529 | vinod ravan borse |  | Joint(Husband and Wife) | MH07001/1/3485[08-04-2022] | 120000 | 4 | 120000 | Completed
81 | DEURBK | MH136833346 | bhatu ragho Deore |  | Joint(Husband and Wife) | MH07001/4/3486[08-04-2022] | 120000 | 3 | 100000 | Completed
82 | DEURBK | MH136973944 | babita balu borse |  | Joint(Husband and Wife) | MH07001/1/3535[15-04-2022] | 120000 | 3 | 100000 | Completed
83 | DEURBK | MH137294788 | amaval punju borse |  | Joint(Husband and Wife) | MH07001/1/3487[08-04-2022] | 120000 | 4 | 120000 | Completed
84 | DEURBK | MH137932683 | sunil bapu salunke |  | Joint(Husband and Wife) | MH07001/1/4602[08-09-2024] | 120000 | 2 | 85000 | Plinth
85 | DEURBK | MH137932689 | nanabhau bapu pardhi |  | Joint(Husband and Wife) | MH07001/1/4602[08-09-2024] | 120000 | 2 | 85000 | Lintel Level
86 | DEURBK | MH139152718 | manohar jivan shirassth |  | Joint(Husband and Wife) | MH07001/1/4602[08-09-2024] | 120000 | 3 | 115000 | Lintel Level
87 | DEURBK | MH139152768 | mamohar vishwas nrekar |  | Joint(Husband and Wife) | MH07001/2/4251[22-07-2022] | 120000 | 1 | 15000 | Completed
88 | DEURBK | MH139517664 | hiraman nimba gavle |  | Joint(Husband and Wife) | MH07001/4/3733[01-05-2022] | 120000 | 4 | 120000 | Completed
89 | DEURBK | MH140611452 | bharat bhaskar bagale |  | Joint(Husband and Wife) | MH07001/1/4962[11-09-2024] | 120000 | 2 | 85000 | Plinth
90 | DEURBK | MH150219709 | daga sonu borse |  | Joint(Husband and Wife) | MH07001/4/3424[04-04-2022] | 120000 | 2 | 60000 | Completed